## Data Integration Plan (hidden)
TYPE | Activity | Overall Target Date | Owner(s) | KCH Target Date | KCH Actual | KCH Estimate | KCH | UCLH Target Date | UCLH | Imperial Target Date | Imperial | GSTT Target Date | GSTT | SLAM Target Date | SLAM | UHS Target Date | UHS | RBH Target Dates | RBH
Data Discovery | Kick-Off Meetings |  | AIC |  |  |  | Done |  | Done |  | Done |  | Done |  | To Do | 2022-07-29 | To Do |  | To Do
Data Discovery | Distribution of Trust Data Questionnaires |  | AD/AIC |  |  |  | Done |  | Done |  | Done |  | Done |  | To Do |  | To Do |  | To Do
Data Discovery | Questionnaire Responses Received from Trust |  | Trust | 2022-07-08 |  |  | Done | 2022-07-08 | Awaiting Response | 2022-07-08 | Done | 2022-07-08 | Done |  | To Do |  | To Do |  | To Do
Data Discovery | Initial meeting with identified Trust Contact |  | Trust/AD/AIC | 2022-07-29 |  | 2hrs | Meeting Scheduled | 2022-07-29 | To Do | 2022-07-29 | Meeting Scheduled | 2022-07-29 | Meeting Scheduled |  | To Do |  | To Do |  | To Do
Data Discovery | Data Catalogue Complete for Trust with identified Trust Systems |  | Trust/AD/AIC |  |  | 1 day | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do
In-bound Pipeline Development | Trust development patient data - historic (Tables set up for T-FLIP etc) | 2 days | Trust Integration Teams |  |  |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do
In-bound Pipeline Development | Trust Patient data - PAS HL7 Message configuration - ongoing (set-up/reroute datafeed) |  | Trust Integration Teams |  |  |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do
In-bound Pipeline Development | Trust development observation data - historic (Tables set up for T-FLIP etc) |  | Trust Integration Teams |  |  |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do
In-bound Pipeline Development | Trust observation data - PAS HL7 Message configuration - ongoing (set-up/reroute datafeed) |  | Trust Integration Teams |  |  |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do
In-bound Pipeline Development | Trust development unstructured data - historic |  | Trust Integration Teams |  |  |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do
In-bound Pipeline Development | Trust development unstructured data - ongoing |  | Trust Integration Teams |  |  |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do
Integration Development | TIE components for FHIR generation of real time and historic patient data (Demographics) |  | AD Integration Team | Not Trust Specific | Not Trust Specific |  | In Progress | Not Trust Specific | In Progress | Not Trust Specific | In Progress | Not Trust Specific | In Progress | Not Trust Specific | In Progress | Not Trust Specific | In Progress | Not Trust Specific | In Progress
Integration Development | Set up HAPI FHIR Server for Mock endpoint |  | AD Integration Team | Not Trust Specific | Not Trust Specific |  | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do
Integration Development | Internal Full end to end testing of Demographic components |  | AD Integration Team | Not Trust Specific | Not Trust Specific |  | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do
Integration Development | Create Mock database table for observation data |  | AD Integration Team | Not Trust Specific | Not Trust Specific |  | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do
Integration Development | Create mock data creation components for observation data |  | AD Integration Team | Not Trust Specific | Not Trust Specific |  | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do
Integration Development | Create TIE Component for observation data ingestion (Historic and real time) |  | AD Integration Team | Not Trust Specific | Not Trust Specific |  | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do
Integration Development | Create TIE component for generation of Observation FHIR resource |  | AD Integration Team | Not Trust Specific | Not Trust Specific |  | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do
Integration Development | Internal Full end to end to testing of observation components |  | AD Integration Team | Not Trust Specific | Not Trust Specific |  | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do
Integration Development | Unstructured |  | AD Integration Team | Not Trust Specific | Not Trust Specific |  | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do | Not Trust Specific | To Do
Data Ingestion Testing | Identify Integration Resource for Support with Testing |  | AD/AIC |  |  |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do
Data Ingestion Testing | Real Data End-to-End test - Demographic |  | AD/Trust Integration Team |  |  |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do
Data Ingestion Testing | Real Data End-to-End test - Observation |  | AD/Trust Integration Team |  |  |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do
Data Ingestion Testing | Real Data End-to-End test - Unstructured |  | AD/Trust Integration Team |  |  |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do
Start SE Data Population | Demographic Data |  | Trust/AD/AIC |  |  |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do
Start SE Data Population | Imagining Data |  | Trust/AD/AIC |  |  |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do
Start SE Data Population | Unstructured Data |  | Trust/AD/AIC |  |  |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do |  | To Do

## ValidationSheet
Core Data Requirements
| Number of 'Core' Data Requirements per pathway. |  |  |  |  | Structured Data Items | 12
| Stroke | Heart Failure 4D | Heart Failure | Lung Cancer | Prostate Cancer | Unstructured Data Items | 38
| 14 | 15 | 10 | 10 | 6
Structured | 5 | 5 | 4 | 7 | 3
Unstructured | 9 | 10 | 6 | 4 | 4
Optional Data Requirements
Number of 'Optional' Data Requirements per pathway.
| Stroke | Heart Failure 4D | Heart Failure | Lung Cancer | Prostate Cancer
| 0 | 0 | 0 | 13 | 1
Structured | 0 | 0 | 0 | 4 | 0
Unstructured | 0 | 0 | 0 | 8 | 0
Data Items by System by Trust
Number of data items where system has been identified
| KCH | UCLH | GSTT | Imperial
| 49 | 0 | 0 | 0
Number of data items where system has not been identified
| KCH | UCLH | GSTT | Imperial
| 1 | 50 | 50 | 50

## Data Catalogue Master
Data Requirement |  |  |  | Shortlisted Models |  |  |  |  | Data Source -> | Generic Guide / Notes |  |  |  | Location notes | KCH Ben Fidler Vivek Verma |  |  |  | UCLH |  |  |  | GSTT |  |  |  | Imperial
Type | Point | Example Data Point | Template | Stroke | Heart Failure 4D | Heart Failure | Lung Cancer | Prostate Cancer | Structured / Unstructured | Generic Trust Location | Existing National Dataset | Notes | Existing Event-Based Datafeed |  | System | Details | Point of Contact | TIE Notes | System | Details | Point of Contact | TIE Notes | System | Details | Point of Contact | TIE Notes | System | Details | Point of Contact | TIE Notes
Medical History | Accession Number | 12345678910111213141 | visit | Core | Core | Core | Core | Core | Structured | PAS RIS/PACS |  |  |  |  | In Cogstack multimedia index or PACS |  | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [7 empty] | Godfrey Chisinga |  |  |  | Ben Glampson
Demographic | NHS Number | 1234567890 | all | Core | Core | Core | Core | Core | Structured | PAS/EPR | CDS |  |  |  | In multiple Cogstack indices | as PAS not easily accessible | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [7 empty] | Aaron Duval |  |  |  | Ben Glampson
Demographic | Age / Date of birth | 2004-01-01 | demographic | Core | Core |  | Core |  | Structured | PAS | CDS |  | 1 |  | In multiple Cogstack indices | as PAS not easily accessible | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Ben Glampson
Demographic | Sex/Gender | 2 | demographic |  | Core |  | Optional |  | Structured | PAS | CDS |  | 1 |  | In multiple Cogstack indices | as PAS not easily accessible | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Ben Glampson
Demographic | Ethnicity | B | demographic |  |  |  | Optional |  | Structured | PAS | CDS |  | 1 |  | In multiple Cogstack indices | as PAS not easily accessible | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Outcome | Date of death | 2004-01-30 | demographic | Core | Core | Core | Core |  | Structured | PAS |  |  |  |  | In multiple Cogstack indices | as PAS not easily accessible | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Ben Glampson
Demographic | Height |  | demographic |  |  |  | Optional |  | Structured | Obs or EPR |  |  |  |  | In Cogstack Obs index |  | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Lesley Honeyfield
Demographic | Weight (nearest time of diagnosis) |  | demographic |  |  |  | Optional |  | Structured | Obs or EPR | CDS |  |  |  | In Cogstack Obs index |  | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Demographic | Smoking Status | 4 |  |  |  |  | Optional |  | Unstructured | Somerset Cancer Registry | COSD |  |  |  | In Cogstack Obs index; Else from MedCat Freetext | Validation training has been done with MedCat | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Lesley Honeyfield
Demographic | Smoking History | [5 empty] | Optional |  | Unstructured | Somerset Cancer Registry | COSD |  |  |  | In Cogstack Obs index; Else from text via MedCatServ | Validation training has been done with MedCat | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Diagnosis | Heart Failure (HFpEF and HFrEF) | Heart failure with reduced ejection fraction | diagnosis |  | Core |  |  |  | Unstructured |  | CDS (ICD10 coded), NICOR entry |  |  |  | In Cogstack Obs index; Else from text via MedCatServ | Validation training has been done with MedCat | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Ben Glampson
Diagnosis | Heart Failure |  | diagnosis |  |  | Core |  |  | Unstructured |  | CDS (ICD10 coded), NICOR entry | Heart failure diagnosis (ICD-10 codes: I20-I25, I40-I43, I50 (all subclases)) |  |  | In Cogstack Obs index; Else from text via MedCatServ | Validation training has been done with MedCat | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Diagnosis | Dilated cardiomyopathy |  | diagnosis |  | Core |  |  |  | Unstructured | Cardiac registry system | NICOR |  |  |  | In Cogstack Obs index; Else from text via MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Ben Glampson
Diagnosis | Coronary artery disease |  | diagnosis |  | Core |  |  |  | Unstructured | EPR | NACR |  |  |  | In Cogstack Obs index; Else from text via MedCatServ | Validation training has been done with MedCat | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Ben Glampson
Diagnosis | Pulmonary hypertension |  | diagnosis |  | Core |  |  |  | Unstructured | EPR, Letters, cardiac registry system | NICOR | Not specifically pulmonary |  |  | In Cogstack Obs index; Else from text via MedCatServ | Validation training has been done with MedCat | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Ben Glampson
Medical History | Major adverse cardiac events |  | diagnosis |  | Core |  |  |  | Unstructured | Cardiac registry system, EPR | NACR |  |  |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Ben Glampson
Medical History | New York Heart Association functional class | Class I |  |  | Core |  |  |  | Unstructured | Cardiac registry system | NICOR |  |  |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Ben Glampson
Medical History | Six minute walk distance | 250m |  |  | Core |  |  |  | Unstructured | cardiac registry system, observations system | NACR |  |  |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Ben Glampson
Medical History | BSA (Body Surface Area)? | 2.060m2 |  |  | Core |  |  |  | Unstructured |  |  | To confirm with researcher (BSA appears to be retired from NHS data model) |  |  | To be calculated from Height/Weight |  | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | Date of outcome | 2018-01-25 | diagnosis |  | Core |  |  |  | Structured | PAS |  |  |  |  | ????? Unclear what the outcome is |  | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Ben Glampson
Medical History | Date of diagnosis | 2018-01-25 | diagnosis |  |  |  | Core |  | Structured | PAS? |  |  |  |  | ????? Unclear what the diagnosis is |  | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | Tumour histological subtype - non-small cell lung cancer - squamous cell | [5 empty] | Core |  | Unstructured | EPR notes, letters, EPR Problem List, Somerset, Order Comms | COSD | Event-based semi-structured text if looking at histology reports | 1 |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | Tumour histological subtype - non-small cell lung cancer - adenocarcinoma | [5 empty] | Core |  | Unstructured | EPR notes, letters, EPR Problem List, Somerset, Order Comms | COSD | Event-based semi-structured text if looking at histology reports | 1 |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Lesley Honeyfield
Medical History | Tumour histological subtype - non-small cell lung cancer - non-specific non-small cell | [5 empty] | Core |  | Unstructured | EPR notes, letters, EPR Problem List, Somerset, Order Comms | COSD | Event-based semi-structured text if looking at histology reports | 1 |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Images | CT / MRI Scan (description of images) |  | visit | Core | Core | Core | Core | Core | Structured | PACS |  | Scans of relevant body area | 1 |  | From PACS (+/- Xnat) |  | AI Centre PACS manager (Sharaf Ayinla) | [11 empty] | Ben Glampson
Images | Peak kV of the scan | 80kVp | visit |  |  |  | Optional |  | Structured | RIS. PACS |  | Kilovoltage Peak (CT) | 1 |  |  |  | AI Centre PACS manager (Sharaf Ayinla)
Medical History | Pre-treatment tumour staging (TNM) | T4N3M1a |  |  |  |  | Core |  | Unstructured | EPR Notes, Somerset, letters | COSD |  |  |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | Tumour Expression - p68, p40, CH5, TF-1, CK7, CK20, CD56, Synaptophysin, cam5.2, CDX2, NApsin-A, AKL | [5 empty] | Optional |  | Unstructured | LIMS |  |  |  |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | Mutations - EGFR, KRAS, BRAF, PIK3Ca, NRAS, Other mutations | [5 empty] | Optional |  | Unstructured | GLIMS, LIMS, Order Comms, EPR, Letters, Somerset | COSD | Event-based semi-structured text if looking at histology reports | 1 |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Lesley Honeyfield
Medical History | PET-CT Data |  | visit |  |  |  | Optional |  | Unstructured | PACS |  |  | 1 |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | Histology sample type (cytology, surgical specimen or core biopsy) | [5 empty] | Optional |  | Unstructured | Order comms, Somerset | COSD |  | 1 |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | Type of Biopsy | 12 | [5 empty] | Optional | Unstructured | LIMS | COSD | DIagnostic procedue includes biopsy |  |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | Histology - Keratinisation (If squamous cell), Mucinous/non mucinous/mixed (If adenocarcinoma), Predominant pattern (lepidic, acinar etc.), Secondary pattern, Tertiary pattern | [5 empty] | Optional |  | Unstructured | Order comms, LIMS |  | Event-based semi-structured text if looking at histology reports | 1 |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | Other antibodiues - PD-L1% (total), PDL1 0, PDL1 1+, PDL1 2+, PDL1 3+, Lymphoid infiltrates (2+, 1+, etc.) | 2 |  |  |  |  | Optional |  | Unstructured | Order comms, LIMS |  | Event-based semi-structured text if looking at histology reports | 1 |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | Lesion Contours | [6 empty] | Core | Unstructured | RIS reports |  |  |  |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | Gleason Grade (Lesion) | 4+3 | [5 empty] | Core | Unstructured | RIS reports |  |  |  |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | PSA Blood Result (at point of images) | 4 ng/mL | [5 empty] | Core | Unstructured | Order Comms, letters, RIS Reports |  |  |  |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Lesley Honeyfield
Medical History | Lesion Type |  |  | Core |  |  |  |  | Unstructured | RIS reports |  |  |  |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | Comorbidities |  | diagnosis | Core |  | Core |  |  | Unstructured | Cardiology registry system, letters, EPR | NACR |  |  |  | To be defined in SNOMED to get from MedCatServ |  | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | Anticoagulant use |  | medication | Core |  |  |  |  | Unstructured | EPMA, letters, AC dosing system |  |  |  |  | To be defined in SNOMED to get from MedCatServ | Validation training has been done with MedCat | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | Arteriovenous malformation |  | diagnosis | Core |  |  |  |  | Unstructured | EPR notes, letters | CDS? |  |  |  | To be defined in SNOMED to get from MedCatServ | Validation training has been done with MedCat | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | Tumour |  | diagnosis | Core |  |  |  |  | Unstructured | EPR notes, letters | CDS? | Unclear (any Tumour?) Would Brain Tumour be more specific? |  |  | To be defined in SNOMED to get from MedCatServ | Validation training has been done with MedCat | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | Cavernoma |  | diagnosis | Core |  |  |  |  | Unstructured | EPR notes, letters |  | cavernous angiomas cerebral cavernous malformation |  |  | To be defined in SNOMED to get from MedCatServ | Validation training has been done with MedCat | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | Intracranial aneurysm |  | diagnosis | Core |  |  |  |  | Unstructured | EPR notes, letters | CDS |  |  |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | Haemorrhagic transformation of an infarct |  | diagnosis | Core |  |  |  |  | Unstructured | EPR notes, letters | CDS | Hemorrhagic infarction/ infarct |  |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY)
Medical History | Major head trauma |  | diagnosis | Core |  |  |  |  | Unstructured | EPR notes, letters | TARN SSNAP | May be listed as Major Head Injury |  |  | To be defined in SNOMED to get from MedCatServ | No validation training has been done with MedCat for this code so performance unknown | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Lesley Honeyfield
Images | CMR Scans (cardiac MRI scans) |  | visit |  |  | Core |  |  | Unstructured | PACS |  |  |  |  | From PACS (+/- Xnat) |  | AI Centre PACS manager (Sharaf Ayinla) | [11 empty] | Lesley Honeyfield
Medical History | Hospital Admissions |  | visit |  |  | Core |  |  | Unstructured | PAS | NICOR | Episodes of hospital admission and diagnosis of admission (ICD code?) |  |  | In multiple Cogstack indices | Date of inpatient events are stored as metadata to e-noting documents so obtainable from Cogstack as unique episode_dates | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Lesley Honeyfield
Medical History | Hospital Admission Date | CCYY-MM-DD | visit |  |  | Core |  |  | Unstructured | PAS | NICOR |  |  |  | In multiple Cogstack indices | Date of inpatient events are stored as metadata to e-noting documents so obtainable from Cogstack as unique episode_dates | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Lesley Honeyfield
Medications | Medications |  | medication |  |  | Core |  |  | Unstructured | EPMA or letters, Cardiac Registry System | NICOR | often paper 'Kardex' charts |  |  | To be defined in SNOMED to get from MedCatServ |  | Cogstack team (KCH: MohammadAl Agil, Samora Hunter; supported by Anthony Shek, JoshuaAY) | [11 empty] | Lesley Honeyfield
[13 empty] | Count of systems identified for data items |  | 49 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[13 empty] | Count of unidentifed data items |  | 1 |  |  |  | 50 |  |  |  | 50 |  |  |  | 50

## Defn
Systems |  | Examples
PAS | Patient Administration System | System C | May be shared function with EPR
OPbs or EPR | Electonic Patient Record | PatientTrak, Carenotes, Cerner, DXC (Lorenzo) | Some systems manage observations in seperaate systems, some log directly into EPR
AC Dosing system | System for prescribing antocoagualnt use based on INR results | Dawn AC
COSD | Cancer Outcomes and Services Dataset
CDS | Commissioning Dataset
RIS | Radiology Information System | CHRIS, EPIC radiant | Manages scheduling, reporting
EPMA | Electronic Prescribing and Medicines Administration | Cerner or WellSky
TARN | Trauma Audit and Research Network
SCR | Somerset Cancer Register
HFpEF | Heart failure with preserved ejection fraction
HFrEF | Heart failure or heart failure with reduced ejection fraction
NICOR | National Institute for Cardiovascular Outcomes Research.
NACR | National Audit of Cardiac Rehabilitation
Order Comms | Electronic Order Communications Management | Clinisys
Obs | Observations |  | Variety of obs systems in use
| Cardiac registry system | Dendrite | sometimes custom system for managing data and registry submissions
SSNAP | Sentinel Stroke National Audit Programme
LIMS | Laboratory Information Management Systems | Agilent, Starlims, Accelrys, iSoft and CliniSys (WinPath Enterprise)

## Schema
Data Item
Smoking status | Common FLIP Schema | KCH | GSTT | ULCH | Imperial
Value
- code | 1 | 1 | 77176002
- description | Never Smoked | Never smoked | Not Smoked
Code system | FIXED: NHS DD National codes | NHS DD National codes | SNCT
effectiveDate | FORMAT: ISO
Smoking History | Tobacco Use
Heart Failure (HFpEF and HFrEF)
Dilated cardiomyopathy
Coronary artery disease
Pulmonary hypertension
Major adverse cardiac events
New York Heart Association functional class
Six minute walk distance
Date of outcome
Date of diagnosis

## diagnostic event
field | description | data dictionary | data type | example | OMOP
NHS Number | the unique NHS number for the patient. This will be used to confirm opt-out status and will be pseudonymised before storing in OMOP CDM research database | https://www.datadictionary.nhs.uk/data_elements/nhs_number.html?hl=nhs%2Cnumber | int(10) | 1234567890 | person.person_id
Scan Date | the date the scan occurred | https://www.datadictionary.nhs.uk/attributes/activity_date.html?hl=date | yyyy-MM-dd | 2020-01-01 | ?
Radiological Accession Number | a reference to the DICOM images generated from the study / scan of the patient | https://www.datadictionary.nhs.uk/data_elements/radiological_accession_number.html?hl=accession | varchar(20) | RJZ2958331 | ?
Scan Type | the type of scan that the Radiological Accession Number refers to |  | enum(MRI, CT, ULTRASOUND, PET) | MRI | ?
Peak kV of Scan | the peak potential applied to the x-ray tube |  | decimal(8,4) | 60 | ?

## demographic
field | description | data dictionary | data type | example | OMOP
NHS Number | the unique NHS number for the patient. This will be used to confirm opt-out status and will be pseudonymised before storing in OMOP CDM research database | https://www.datadictionary.nhs.uk/data_elements/nhs_number.html?hl=nhs%2Cnumber | int(10) | 1234567890 | person.person_id
Date of Birth | the date on which a person is born or officially deemed to have been born | https://www.datadictionary.nhs.uk/attributes/person_birth_date.html?hl=date%2Cbirth | yyyy-mm-dd | 2000-01-01 | person.year_of_birth, person. person.month_of_birth, person.day_of_birth
Person Gender Code | the gender code of the person | https://www.datadictionary.nhs.uk/attributes/person_gender_code.html | int(1) - ENUM(0,1,2,9) | 2 | person.gender_concept_id
Ethnic Category Code | the ethnicity of a person, as specified by the person | https://www.datadictionary.nhs.uk/attributes/ethnic_category_code_2001.html | varchar(1) | D | person.ethnicity_concept_id
Person Death Date | the date on which a person died or is officially deemed to have died | https://www.datadictionary.nhs.uk/attributes/person_death_date.html | yyyy-mm-dd | 2020-01-01 | death.death_date

## diagnosis
field | description | data dictionary | data type | example
NHS Number | the unique NHS number for the patient. This will be used to confirm opt-out status and will be pseudonymised before storing in OMOP CDM research database | https://www.datadictionary.nhs.uk/data_elements/nhs_number.html?hl=nhs%2Cnumber | int(10) | 1234567890
Document Date | the date the document was last updated (discharge datetime / last updated datetime) | https://www.datadictionary.nhs.uk/attributes/activity_date.html?hl=date | yyyy-MM-dd | 2020-01-01
Document ID | a unique reference for the document |  | varchar(20) | 3444RJHUI
Document Text | the body text of the generated document |  | text | Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua. Ut enim ad minim veniam, quis nostrud exercitation ullamco laboris nisi ut aliquip ex ea commodo consequat.
*diagnosis data will be expected through the unstructured data route - MedCAT NLP analysis will generate the diagnosis outcomes

## Data_Questions
Question | Pathway | Response
Anticoagulant use (Stroke Model) - given the variety & number of A/C drugs; how will Trusts determine if the patient was prescribed A/C medication (is there a marker on the EPMA or does the Trust simply need to provide details of all medications the patient was on? Is the use current/historic or both?
Comorbidities - is this is any other accompanying disease or condition that patient has been diagnosed with (even if seemingly unrelated) e.g. cardiomyopathy and narcolepsy)
Lesion contours (shapes?) Could this mean lesion size? | Prostate (Michaela)
Gleason Grade - Primary? | Prostate (Michaela)
BSA, if this is Body Surface Area - appears to be retired from NHS Data Model since 2012 - are there alternatives to obtain, such as BMI, height/weight? | Heart 4D (Declan) | Yes - BSA is body surface area. To confirm if alternatives need to be obtained if BSA not available (when we meet)
Data items that may have multiple different entries over time (for example | Prostate